## Executive Summary
Executive Summary
| test_project |  |  | Project Manager:
Project Number: | test_project_number |  |  | Project QS:
Date: | 1970-01-01
Project Start Date: |  |  |  | Gross Internal Floor Area:
Project PC Date:
Project Week No | 1 of 25
Project Status +/- Weeks | -4
Variation No's
Sales Account |  | Now | Prev | This Month | Previous | Movement | %
Order Value (nett of prov Sums & MCD) |  |  |  | 6293357 |  | 6293357
Agreed Variations |  | 1 |  | 25450 |  | 25450 | 0%
Budget variations |  | 1 |  | 114 |  | 114 | 0%
Submitted Variations |  | 1 |  | 56787 |  | 56787 | 0%
| Variations No. | 3 | 0
| Sale SubTotal |  |  | 6375708 | 0 | 6375708 | 0%
Reserves
Agreed Variations |  |  |  | -254.5 |  | -254.5 | 0%
Budget variations |  |  |  | -57 |  | -57 | 0%
Submitted Variations |  |  |  | -5678.7 |  | -5678.7 | 0%
| Reserve Total |  |  | -5990.2 | 0 | -5990.2 | 0%
Contra Charges |  |  |  | -9889 |  | -9889 | 0%
| Forecast SaleTotal |  |  | 6359828.8 | 0 | 6359828.8 | 0%
Cost analysis |  |  |  | This Month | Previous | Movement | %
Current Cost |  |  |  | 54874 |  | 54874 | 0%
Cost to Complete |  |  |  | 87899 |  | 87899 | 0%
| Cost Sub Total |  |  | 142773 | 0 | 142773 | 0%
Defects Provision |  |  |  | 68998 |  | 68998 | 0%
| Forecast CostTotal |  |  | 211771 | 0 | 211771 | 0%
Margin analysis |  |  |  | This Month | Previous | Movement | %
Contract Contribution |  |  |  | 6148057.8 |  | 6148057.8 | 0%
Identified Betterments / Risks |  |  |  | 5587 |  | 5587 | 0%
Regional Director & Commerical Managers View |  |  |  | 147 |  | 147 | 0%
| Forecast MarginTotal |  |  | 6153791.8 | 0 | 6153791.8 | 0%
Margin % |  |  |  | 2906% | 0% | 2906% | 0%
Tender Margin % |  |  |  | 3.83% |  | 3.83% | 0%
Cash Recovery |  |  |  | This Month | Previous | Movement | %
Latest Application |  |  |  | 6598787 |  | 6598787 | 0%
Certificated - Cash Rec'd |  |  |  | 0 | 0 | 0 | 0%
Certificated - Cash not Rec'd |  |  |  | 1144 |  | 1144 | 0%
Total Certified |  |  |  | 1144 | 0 | 1144 | 0%
Retention Total |  |  |  | 0 | 0 | 0 | 0%
Retention Released |  |  |  | 0 | 0 | 0 | 0%
Retention Held |  |  |  | 0 | 0 | 0 | 0%
Outstanding Debtor (Current cost + Margin less Certified) |  |  |  | 1648297.5812 | 0 | 1648297.5812 | 0%
Gross Exposure (Current cost + Margin less Certified + Retention) |  |  |  | 1648297.5812 | 0 | 1648297.5812 | 0%
Open Book (P21+ etc) |  | Fee |  | This Month | Previous | Movement | %
Original GMP -Order Value (nett of prov Sums & MCD) |  |  |  | 6293357 |  | 6293357 | 0%
Original GMP with CE's |  |  |  | 6359828.8 |  | 6359828.8 | 0%
Forecast GMP (current cost + fee) |  | 7.5% |  | 227653.825 |  | 227653.825 | 0%
Variance |  |  |  | 6132174.975 | 0 | 6132174.975 | 0%